## Slide 1: Client Delivery
Current State
Future State
Plan to get there
Notes: You’re here today so we can show you how we plan to structure of client accounts moving forward.
There have been many changes within our company during the last year.
Our mission, structure, methodology and processes are evolving.
All of this will enable us to provide a stronger, more comprehensive service to our clients.

## Slide 2: Client Retention is a Top Priority
Digital Account Management
The ability to keep clients consistently happy
  To OWN the account
  To care about the client
  To know what the client needs
Be able to constantly identify ways to increase their business’s revenue using digital solutions
Winning repeat business from existing clients
Extending their agency’s reach into the client’s business

## Slide 3: Account Management Expectations
Take on and own the client as a new account
Build rapport and trust with the client
Deal with any non-project related requests a client may send through
Pro-actively spot opportunities, suggest and sell genuinely useful solutions to the client
Role of Digital Account Manager
Identify KPIs
Plan strategy
Develop briefs
Manage research resources and providers
Ideate with creative and media partners
Leverage insights
Provide expertise on brand and category
Uncover opportunities
Grow business
Champion new initiatives

## Slide 4: Skill Set
CLIENT MANAGEMENT
Build and maintain client relationships as the primary contact point
Responsible for day-to-day management of clients, requests and accounts
Digital Account Management
Define
Plan
Ideate

## Slide 5: Skill Set
TACTICAL AND STRATEGIC SALES
Identify new sales opportunities within existing accounts
Spearhead client meetings, presentations and account winning client pitches
Provide sales and project documentation including;
  Proposals for upsells, quoting, contracts and budgeting
Lead, write and present client account strategy

## Slide 6: Skill Set
ANALYSIS AND REPORTING
In-depth analysis of web analytics to produce monthly reports with key recommendations for client
Monitoring and understanding their clients markets; be aware of market issues and competitive activity

## Slide 7: Skill Set
CONSULTANCY
Information Architecture, SEO, PPC, and Social Media consultancy
Be their most trusted advisor

## Slide 8: Skill Set
INTERNAL AND PERSONAL
Proven digital creative and technical experience
Manage or work with the production teams to ensure delivery of projects is on time and on budget
Reporting monthly to the agency management team on their activities

## Slide 9: Great Digital Account Management
A burning passion for all things web.
They live and breathe it, during the day and when they go home – they absolutely love it and can’t get enough.

## Slide 10: Skill Set
Ok, so other than the burning passion thing, here’s what else they tend to have:
The ability to provide quality solutions to the client (that they love) because it helps achieve their business aims, but also aligns with their web agency’s business strategy – clever
An honest addiction to the web that enables them to be able to know about and suggest new solutions to clients that are cutting edge and no competitors have started to adopt yet
Enough web design and development knowledge that earns the respect of both production teams and clients
Enough knowledge to handle the whole process mostly alone, right up until the production phase needs to begin
The willingness to personally research any digital topic they need to in order to be able to speak to the client with complete confidence without relying too much on creative or technical production resource

## Slide 11: Structured Process
Right now, we are not following a structured process for taking new or existing client requests and producing quotes
We are running big risks of over selling, under quoting and / or missing critical requirements
– and I guarantee this will invariably result in someone needing to spend more time to fix it!

## Slide 12: Ideas
Weekly account management meetings
For ongoing clients documented call at least 1x per month.
Send a personal note with their email with their report each month about what's new and ideas for opportunities
Set google alerts about their industry, principles, local news, weather... Example: Any restaurant clients should have had a personal email from you about menus showing on serps
Set google alerts about marketing to their clients and share ideas or news...
Know who their main competitors are
Know their industry leaders, follow them...
Post to their social profiles at least 1x per month as yourself. Ifttt.com
Follow their profiles and share their content.
Personally review their site and analytics to identify opportunities.
Share good news
Create relationships with their staff
Send bday cards to clients and staff

## Slide 13: Deliverables
What I want to see
Formal process for account managers
Client profile sheet – To be filled out by each account manager
Client contact report – Monthly
  Call – details
  Shares – Social
  Email correspondence
  Opportunities identified

## Slide 14: Advice Delivery Organization
Account Management Roles
Delivery Executive
  Mark Hazleton
  James Hall
  Heather Langley
Delivery Lead
  Nayra Salamanca
  Jeff Powell
  Carli Odle
Define Consistent Process
Must Scale to all current and future clients
  Small Business
  Enterprise Account
  Nationally Local
  LSS / Technology

## Slide 15: Program Management Office - PMO
Centralized operations unit for a client
Defined organization rather than temporary project team
Partners with client management to work together with set of defined processes
Accountable for:
  Client satisfaction
  Project Delivery
  Communication
  Risk management
  Issue resolution
  Contract administration
Why a Program Office?
  To address the dependencies between projects for a single client
  Provide centralized oversight of all Client work
  Provide organization to insure consistent quality of delivered projects
  Provide a set of process and deliverables that are consistent across all Advice clients

## Slide 16: Program Management Office Structure
Services
Lead
Executive
Sales
Delivery Executive
Strategy
Delivery Lead
Paid Media
Design / Development
SEO / Local
Social
Content
Analytics
CRO

## Slide 17: PMO Executive Team
Consists of Sales, Delivery and Strategy
Pursuit leadership
C-Level client contact
Negotiates contracts (SOW)
Business case development
Delivery Executive
  Project Estimation and Pricing for SOW
  Identifies Additional Opportunities
  Delivery oversight
  Project planning / scheduling
  Project profit and loss ( Project Economics)

## Slide 18: PMO Delivery Lead
Responsible for Client satisfaction - day to day
Manages Task Delivery/Issue Tracking
Coordinate Fulfillment :
  Paid Media
  Design / Development
  SEO / Local
  Social
  Content
  Analytics
  CRO

## Slide 19
Marketing, Sales
Business Development
Marketing
Sales
Channel Partners
Sales + Delivery
Sales + Delivery
PMO Members as needed
Sales + Finance + Delivery
Delivery + Sales
+ PMO Members as needed
Sales + Delivery
Transition to PMO
PROSPECT IDENTIFICATION
LEAD QUALIFICATION
CONSULTATION
PRESENTATION(S)
JUSTIFICATION
PROPOSAL
Schedule
Execute
Delivery
Sales Focus
Delivery Focus
Now
Before
Target
Notes: The client program office is designed to facilitate a smooth transition between Sales and Delivery and to insure the high level of service delivery that our clients demand.

## Slide 21: Delivery Leadership – Next Steps Update
Delivery Execution on existing Clients
  Standing Tuesday meeting to review client delivery status across Advice
Define Client Programs
  Consolidate all Account Lists (Financial, Delivery, Development, SEO, Former SMB, Team Desk) – Publish to Team Desk by March 4th ) – Maintain until migration to Projector (TBD)
  Assign Executive, Team Leads for each client (Publish to Team Desk by March 4th)
  Initial teams will be straight mapping to current assignments, expect to balance the list in the first month.
  Interview Sales to make sure we have adequate transition to Delivery Executive (Friday 2/28)
Integrate PMO with established Process for SOW Deliverables and Estimates
Enterprise Wrike Standards (Under Review by Delivery Organization – Publish by March 6)
  Define, Document, Train, Enforce
Enterprise Reporting Standards (Under Review by Delivery Organization)
  Define, Document, Deliver

## Slide 22: The Program Management Approach
Provide an organization to collaborate with the Client, led by Delivery Lead who supports the PMO Executive team
Support the best practices within Advice Interactive
  The Project Charter Process
  Change Management
  Communication

## Slide 23: What is a Project?
Has a beginning and an end
Is defined by specific objectives (deliverables)
Is conducted by a well-defined organization
Has a single lead who is responsible for its success
Is defined by identifying the starting point and the goal and the route between them
Project Economics
  Has a defined project code to manage time and expenses
  Has a budget defined in a executed Statement of Work, managed thru defined change control procedures

## Slide 24: Project Charter
Charter process is an exercise with the client leadership
Created from fully Executed Statement of Work
Used to guide a project from idea to completion
All projects go through the charter process
A staged process

## Slide 25: Project Charter
Future
  An opportunity has been identified.
Solution Definition
  A team defines the project and create a proposal
Proposed
  Advice has presented a proposal for approval
Scheduled
  Project is approved and a team is being assigned
In Progress
    Advice IG has a team actively working on the project
Complete
    The project has been delivered
Future
Solution Definition
Proposed
Scheduled
Active
Complete
Notes:     Future - An opportunity has been identified. No work is being done, no team has been assigned.
    Solution Definition - The client or PMO has agreed to fund a project solution definition effort. A team has been assigned to define the project and create a proposal. An accounting code is created to track all time used to define the project during the solution definition effort. A limited team is a used; the deliverable from this phase is a proposal to do the project. This phase does not include any analysis, design, comps, or documentation other than what is required to propose the work.
    Proposed - Advice has presented a proposal to the client for approval. This proposal should have an expiration date and specific metrics for when the team can start (i.e. 2 weeks from approval). If resources are named, it should be noted that these resources can't be held for this project while waiting for approval.
    Approved - The client has approved the project proposal. Advice is in the process of defining the project team and setting the project priority. When a team and priority is defined, the project kickoff is scheduled.
    In Progress – Advice has a team working on the project. Weekly status reports are maintained in the PMO database. In addition, scope change documents are maintained in the PMO database as well. Advice is invoicing the project according to the terms of the client service agreement.
    Complete - The project has been delivered. Advice is no longer working on the project. The project code has been retired in the accounting system.
    Cancelled - At any stage in the charter lifecycle, a project may be placed on hold or rejected. The PMO database keeps a history of all projects regardless of status.

## Slide 26: Project Manager
Key client project contact
Responsibilities include:
  Focus on a limited scope
  Communication internally and with client
  Defining a reasonable and acceptable scope of work with project team
  Obtaining client approvals
  Managing a project’s development, internally and externally (high quality, on budget, on time)
  Change management / Issue Management
  Risk management

## Slide 27: Client Change Management
Change is inevitable
    The project management process is creative, and will naturally bring about some change.
Set a tolerance level
    Informal change control can be used when the project budget and schedule are not affected. You still want to document any change to scope.
Manage expectations as well as scope
    Managing the perceptions of team members and the user community is just as important as managing scope.
    Can’t be used for just financial changes, the process is used whenever the Scope (What is being done), Schedule (When is it being done) or Price (What is the cost of the change)
    Always present the client with a choice, never dictate a change to a client.
Notes: 1.1. Change Control Principals
    Change is inevitable. The project management process is creative, and will naturally bring about some change. The project manager's job is to recognize the inherent discovery process in the project and manage the change - not stop it.
    Set a tolerance level. Attempting to formally mange small changes can overwhelm the project manager and distract user management. Informal change control can be used when the project budget and schedule are not affected. All changes to scope are documented in the PMO database for reference purposes.
    Manage expectations as well as scope. To assess and manage change requires the project manager to be sensitive to the people dimension of the project. Managing the perceptions of team members and the user community is just as important as managing scope.

## Slide 28: Change Management Process
Initiation
    A change to the project scope, schedule, or budget is identified
Impact Assessment
    Advice will review the request and document the impact of the change on the current scope, schedule, and project budget.
Approval
    The client project sponsor, and the Advice project manager will sign the change request form.
Implementation
    Advice will incorporate the change into the overall project scope and republish the project schedule, budget, and scope definition documents as needed.
Notes: The purpose of change management is to provide a means for retaining historical change information to enhance future project management efforts. Change management involves the documentation, tracking systems and approval levels necessary to justify and manage a change in the project’s scope. The scope detailed in the project proposal is the baseline against which changes will be controlled. The object of the change control system is to preserve the integrity of the project charter and to allow for the handling of change requests.
It is important to note, that proper change management depends on a detailed project baseline (Statement of Work, Project Baseline, Project Deliverables).
There is a natural discovery process in all projects due to factors such as omissions, mistakes, creativity, misunderstandings, and external influences. This discovery process normally creates pressure to modify the project scope, schedule, or budget. The purpose of scope management process is to constructively mange that pressure.
    Initiation - Generally, anyone within the project organization can request a change by creating a change request in the Advice PMO database. If there is an agreed upon format or template, then that document can be completed and attached to the scope change document in the database.
    Impact Assessment - The Advice project manager will review the request, the impact of the change will be assessed across all knowledge areas. The project manager will document the impact of the change on the current scope, schedule, and project budget. The completed change document is submitted to the project steering committee that is identified during the project initiation.
    Approval - The appropriate project sponsor will ultimately approve or reject the change request. Upon approval of the request, the client project sponsor, and the project manager will sign the change request form. A hard copy of the signed change request will be maintained by the project manger.
    Implementation - The project manager will incorporate the change into the overall project scope and republish the project schedule, budget, and scope definition documents as needed.
    Rejected - The client may close the change request at any point in the process prior to approval. If the change request is rejected, the document is still maintained in the PMO database. However, the scope, schedule, and budget are not affected.

## Slide 29: Client Communication
High-level communications
    Allows a breadth of information to be reviewed at a surface level. This communication often is the catalyst for identifying items that need to be tactically discussed. Typically between client executive and advice executive.
Tactical communications
    Allows a detailed discussion to occur typically about a specified topic. This communication is usually between the team lead and the client.
Notes: High-level communications – This type of communication allows a breadth of information to be reviewed at a surface level. This communication often is the catalyst for identifying items that need to be tactically discussed. This communication is usually between the PMO management and the client sponsors.
Tactical communications – This type of communication allows a detailed discussion to occur typically about a specified topic. This communication is usually between the project manager and the client project manger. This type of communication can be informal and performed using phone, email, fax, and face to face meetings.

## Slide 30: Client Status
Weekly summary of the status of all ongoing and planned projects
Status is summarized by Color
  Red
    Requires Immediate Senior Management Attention
    Team Lead is actively working on resolution
  Yellow
    Requires project sponsor attention
  Green
    Project is on budget, scope, and schedule
Notes: For any project that is in progress, the project manger will submit a weekly status report. The status report will have a summary status with one of the following:
    Red. The project has outstanding issues that require immediate sponsor attention.
    Yellow. The project has outstanding issues that require project sponsor attention.
    Green. The project has no outstanding issues that require project sponsor attention.

## Slide 31: Client Status Reporting
Overall Project Status (Red, Yellow, Green)
Accomplishments This Week
Planned Activities for Next Week
Issues Needing Action
Issues Resolved
Budget
Schedule (High level status of major project milestones)
Notes: In addition to the high level status, the project status report will include the following sections:
    Accomplishments To Date. Milestones with deliverables that were completed and delivered in the past week.
    Planned Activities for Next Week. Milestones with deliverables that will be completed and delivered in the next week.
    Issues Needing Action. Issues needing action by the PMO leadership or Client sponsor
    Issues Resolved. Issues that were resolved in the past week
    Budget. State of the project budget include approved scope changes. Project burn rate.
    Schedule. Description of the state of the project schedule. Can also include a copy of the MS-Project document, HTML report from MS-Project, or a link to the MS-Project document on a server.

## Slide 32: Issue/Task Life Cycle
Identify / Receive
Review / Estimate
Assign
Monitor
Close/Complete Document Resolution
Identify / Receive
Assign
Monitor
Close/ Complete
Review / Estimate
Notes: Receive Issues
All requests for work between Advice and the client will be documented as an issue in the PMO database on the Advice web site. Issues can be received by any contacts such as electronic mail, phone calls, faxes, or mailed requirements will be represent by creating an issue in the PMO database.
Based on input from the issue creator, Advice will assign a priority to each issue. The priority will be used once the issue has been reviewed and categorized.
In addition to issues created by the Client, Advice project personnel will also create issues in the database for Review. Any updates to the issue, including any changes, re-interpretations, clarifications, or decision happening out side the database will be documented in the issue resolution database to ensure proper handling and resolution.
Issue Review
Advice will review each new issue and assign the issue into one of the following six issue categories:
· Functional Bugs - (Site not working as defined)
· Content Changes (Text and Graphics changes)
· Stability and Performance Issues (Requires specialized skillset to resolve)
· Site Enhancements (Changes to functional definition of site)
· Research Request (Requires specialized skillset to resolve)
· PMO process change (new reporting requirements, status call changes, distribution list changes)
At the PMO discretion, this list can be modified to fit the needs of the client.
Issue Assignment
The issue will be assigned to the appropriate Advice and client team members. Once an issue has been assigned to a team, it is the responsibility of each team manager to monitor and resolve issues in their area. The PMO will be responsible for monitoring the success of the issue resolution process.
Issues will be associated with a project. It is up to the project manager to review each issue and determine if a scope change is required. Any issues that affect budget or schedule must have a scope change document approved that covers the change that the issues creates. Multiple issues can be covered by a single scope change document. A document link can be used to reference issues in a scope change.
Document Resolution

## Slide 33: Issue Process Flow
Can be chained to multiple people – each person removes their assignment and adds next person in workflow or reassigns back to task creator
Create
Assignment
Estimate Effort / Schedule
Accept
Confirm Assignment
Validate Schedule
Work
Add Hours Worked
Assign Back to Creator
Close
Validate Task is Done
Add Hours Worked
Review Dependencies
Mark as Complete
Additional Assignments as needed

## Slide 34: Time Tracking Best Practices
Time is captured for a single project
Time is captured in reasonable increments (15, 30, 60 )
Time from multiple sub tasks can be added to a top level task (i.e. Project Management )

## Slide 35: Task Tracking Best Practices
Required
A Task is only for a single project (SOW)
Hours worked on a task are added to the task
Only the task creator should close out a task
Tasks should be for a single effort, don’t include lists of tasks inside a tasks
Tasks always have the root project folder associated with them
Suggestions
Task Naming standards is up to each account
Keep names short and tied to deliverables in the SOW where possible
Task should be high level where possible

## Slide 36: Task Standards
All Clients have a ‘folder’ under the “*Clients” folder in Wrike. The name should be as short as possible, but still recognizable.
A Project is defined by a Statement of Work (SOW) stored in the “Folder Information” for the root folder for that Project
Each task is specific to a single project
Each task is created in the base project folder, additional tags (i.e. sub folders) can be added to allow for easier management of tasks
Only the task creator should mark a task as Complete
When you complete work on a task:
  Add a brief comment to indicate the work is complete
  Add your hours you spent on the task
  Assign it to the person who assigned you the task.
  Remove the assignment to you.
  Do not set task to complete.

## Slide 37: Document Best Practices
SOW goes in the information of the root of the project folder
Final Deliverables go here as well
Managed by Client Team Lead

## Slide 38: Our Client’s Objectives
Maintain synergies across marketing channels
Architect functional websites with brand distinctions and site usability
Acquire and retain customers by providing a superior site experience
Ensuring cost effective and timely internet development services
Utilize new technologies
Develop actionable measurement and reporting
Notes: Why our client’s choose Advice

## Slide 39: Client Challenges
Create a long term relationship over many successful projects
Manage Project Interdependencies
Scope Management
Client participation in account planning (Define Future Opportunities)
Managing growth
Actionable measurement and reporting
Ensuring cost effective and timely service delivery
Notes: Key client challenges